## Projects
Project | Status | Budget | Manager
Tower A | Active | 5000000 | Ali
Tower B | Active | 3000000 | Sara
Villa C | Completed | 1200000 | Omar
Mall D | Pending | 8000000 | Mona

## Deliveries
Project | Item | Location | Required Qty | Delivered Qty | Required Date | Expected Date | Actual Date
Tower A | Cement | Cairo | 500 | 500 | 2026-09-26 | 2026-09-25 | 2026-09-25
Tower B | Steel | Giza | 300 | 120 | 2026-10-06 | 2026-10-09
Villa C | Bricks | Minya | 1000 | 0 | 2026-10-10 | 2026-10-10
Tower A | Sand | Cairo | 200 | 200 | 2026-10-02 | 2026-10-02 | 2026-10-03
Mall D | Paint | Alex | 80 | 0 | 2026-10-17 | 2026-10-15
Villa C | Tiles | Minya | 400 | 100 | 2026-10-07 | 2026-10-07

## Materials
Material | Stock | Unit
Cement | 120 | ton
Steel | 40 | ton

## Suppliers
Name | City
A | Cairo
B | Giza

## Employees
Name | Role
X | Eng

## Equipment
Name | Hours
Crane | 30

## Formwork
Item | Qty
Panel | 10