## Projects
Project ID | Project Name | Client | Project Manager | Location | Start Date | End Date | Status | Total Budget | Total Cost | Progress % | Description
PRJ-001 | New Cairo Infrastructure | Hassan Allam | Ahmed Hassan | New Cairo | 2026-01-01 | 2027-12-31 | Active | 25000000 | 8200000 | 38% | Infrastructure development project
PRJ-002 | West Cairo Water Plant | Water Authority | Mohamed Ali | West Cairo | 2026-03-01 | 2028-06-30 | Active | 40000000 | 10500000 | 26% | Water treatment and pumping project
PRJ-003 | Red Sea Highway | Transport Authority | Omar Salah | Red Sea | 2025-09-01 | 2027-03-31 | Delayed | 18000000 | 11200000 | 62% | Highway and bridge construction project

## Pipelines
Project ID | Project Name | Pipeline ID | Pipeline Name | Description | Budget | Planned Cost | Actual Cost | Remaining Cost | Progress % | Status | End Date
PRJ-001 | New Cairo Infrastructure | PL-001 | Water Network | Main water network works | 9000000 | 8500000 | 3000000 | 6000000 | 33% | Active | 2027-06-30
PRJ-001 | New Cairo Infrastructure | PL-002 | Road Works | Road construction works | 10000000 | 9800000 | 4200000 | 5800000 | 42% | Active | 2027-09-30
PRJ-001 | New Cairo Infrastructure | PL-003 | Drainage | Drainage network works | 6000000 | 5500000 | 1000000 | 5000000 | 18% | Active | 2027-11-30
PRJ-002 | West Cairo Water Plant | PL-004 | Civil Works | Civil construction works | 15000000 | 14000000 | 3500000 | 11500000 | 25% | Active | 2027-12-31
PRJ-002 | West Cairo Water Plant | PL-005 | Mechanical | Mechanical equipment | 12000000 | 11500000 | 3000000 | 9000000 | 20% | Active | 2028-03-31
PRJ-002 | West Cairo Water Plant | PL-006 | Electrical | Electrical systems | 13000000 | 12500000 | 4000000 | 9000000 | 31% | Active | 2028-05-31
PRJ-003 | Red Sea Highway | PL-007 | Earthworks | Earthworks and excavation | 7000000 | 6500000 | 4800000 | 2200000 | 69% | Active | 2026-12-31
PRJ-003 | Red Sea Highway | PL-008 | Bridges | Bridge construction | 6500000 | 6200000 | 5100000 | 1400000 | 78% | Delayed | 2026-11-30
PRJ-003 | Red Sea Highway | PL-009 | Finishing | Finishing and road marking | 4500000 | 4200000 | 1300000 | 3200000 | 35% | Not Started | 2027-02-28

## Pipeline Details
Project ID | Project Name | Pipeline ID | Pipeline Name | Category | Item | Planned Cost | Actual Cost | Date
PRJ-001 | New Cairo Infrastructure | PL-001 | Water Network | Pipes | Main water pipes | 3000000 | 1800000 | 2026-02-15
PRJ-001 | New Cairo Infrastructure | PL-001 | Water Network | Labor | Installation labor | 2500000 | 700000 | 2026-04-20
PRJ-001 | New Cairo Infrastructure | PL-001 | Water Network | Materials | Valves and fittings | 1500000 | 500000 | 2026-06-10
PRJ-001 | New Cairo Infrastructure | PL-002 | Road Works | Materials | Asphalt | 3500000 | 1600000 | 2026-03-12
PRJ-001 | New Cairo Infrastructure | PL-002 | Road Works | Labor | Road construction labor | 3000000 | 1200000 | 2026-05-18
PRJ-002 | West Cairo Water Plant | PL-004 | Civil Works | Concrete | Concrete works | 6000000 | 1500000 | 2026-04-05
PRJ-002 | West Cairo Water Plant | PL-004 | Civil Works | Steel | Structural steel | 4000000 | 1200000 | 2026-06-22
PRJ-002 | West Cairo Water Plant | PL-005 | Mechanical | Equipment | Pumps and equipment | 7000000 | 1800000 | 2026-07-15
PRJ-002 | West Cairo Water Plant | PL-006 | Electrical | Equipment | Electrical panels | 6000000 | 2000000 | 2026-08-01
PRJ-003 | Red Sea Highway | PL-007 | Earthworks | Equipment | Excavation equipment | 3000000 | 2400000 | 2026-02-10
PRJ-003 | Red Sea Highway | PL-008 | Bridges | Concrete | Bridge concrete | 3500000 | 3000000 | 2026-03-25

## Deliveries
Project | Item | Location | Required Qty | Delivered Qty | Remaining Qty | Required Date | Expected Date | Actual Date | Status
New Cairo Infrastructure | Pipes | Zone A | 1000 | 800 | 200 | 2026-10-10 | 2026-10-08 | 2026-10-07 | Delivered
New Cairo Infrastructure | Cables | Zone B | 500 | 300 | 200 | 2026-10-15 | 2026-10-18 |  | Delayed
West Cairo Water Plant | Pumps | Plant Area | 20 | 12 | 8 | 2026-11-01 | 2026-11-01 |  | Pending / On Track
Red Sea Highway | Steel | Bridge 1 | 800 | 500 | 300 | 2026-10-20 | 2026-10-20 |  | Pending / On Track